## V3.1 — Proposed
AGV MIAMI
EXPERIENTIAL FABRICATION & PRODUCTION · PROPOSAL INVOICE · Version 3.1
PRODUCER | CLIENT | PROJECT
AGV Miami, LLC | Gymshark Ltd. | GS-PHONEBOX-001
1440 Church St | Attn: Authorized Billing Contact | Version 3.1
Bohemia, NY 11716 | c/o Ominto Studio | Issue Date: May 7, 2026
jclarkson@agvmiami.com |  | Activation: Friday, July 17, 2026, 11 AM–8 PM
info@agoravisuals.com |  | Venue: Euclid Oval, Lincoln Road Mall
3.1 SCOPE
V3.1 proposed update — yellow Miami palette throughout (paint, vinyl, lightbox, signage), operating hours extended to 11 AM–8 PM, back-of-house staff compartment with separate back access door, simplified consumer walkie-talkie pair, basic selfie/belfie mounts (no ring lights), Content Capture & Media Handoff Platform removed, 200-unit custom packaging added, and a local NYC install crew + in-store fixture setup + store wayfinding for the post-Miami delivery. Activation remains Friday, July 17, 2026 at Euclid Oval, Lincoln Road Mall (Saturday, July 18 held as a weather contingency).
Phase 01 — The Phone Box (Painted Yellow Finish)
Phone Box Structural Shell | Custom scenic fabrication, marine-grade paint in Miami yellow (PMS TBC by Ominto), two-piece modular construction | 14500
4-Sided Illuminated Lightbox Signage | LED-backlit translucent face panels on all four sides; weatherproof housing | 6800
Glass & Semi-Transparent Vinyl Panels | Tempered glass on front door + sides with custom-printed yellow-palette privacy vinyl | 2900
Painted Yellow Interior (V3.1 — yellow palette) | Four-wall matte paint finish in Miami yellow, dimensional bum mirror with scripted messaging. Yellow PMS callout to be confirmed by Ominto. | 3800
Concealed Sliding Prize Door | Motorised, colour-matched, no visible handle on public face — for slot-style product handoff from the back-of-house staff compartment | 3400
Interior Finishes | Aluminium chequer-plate flooring, dome light, guest seat, branded analogue phone | 2750
Engineering, Structural Calcs & Shop Drawings | Wind-load, ballast plan, electrical schematics, CAD shop drawings, venue-compliance package | 4000
Back-of-House Compartment + Back Access Door (V3.1 — new) | Interior partition wall + hinged back-access door + small staff stoop, allowing one Gymshark-supplied team member to occupy a private back compartment and dispense product through the motorised slot to the guest. Talent supplied by Client per the proposal exclusions. | 2400
Subtotal — The Phone Box |  | 40550
Phase 02 — Interactive Tech (V3.1 — simplified)
Pre-Recorded Call-Response (IVR) System | Multi-branch scripting, licensed voice talent, keypad mapping, redundant win/lose logic, QA | 5500
Walkie-Talkie Pair (V3.1 — consumer-grade) | Off-the-shelf Motorola pair: one inside the booth for the guest, one with the on-site Gymshark athlete. Includes spares. Replaces the V3.0 dual-mode encrypted relay with backup uplink. | 400
Ceiling Dual Camera System | Two 4K video+audio cameras, cloud storage, live-preview monitoring, disclosure signage | 4500
Selfie & Belfie Mobile Mounts (V3.1 — basic) | Two simple wall-mounted phone holders for guests' own phones. Painted to match interior. Replaces the V3.0 motion-triggered ring-light variant. | 600
Thermal Voucher Printer & Shelf Mount | Dual-speed thermal ticket printer, wrapped, redundant roll inventory, firmware | 2800
(Removed in V3.1) Content Capture & Media Handoff Platform | Cloud workspace + colour-corrected proxies + 48-hour delivery — REMOVED at Client request; Client supplies own media pipeline. Raw camera files handed over on drive at strike at no extra cost. | 0
Subtotal — Interactive Tech |  | 13800
Phase 03 — Branding, Signage & Consumables (V3.1 — packaging added)
Disclosure & Wayfinding Signage | Camera-disclosure sign, queue management decals, brand lockup callouts in yellow palette | 950
Venue Dressing Kit | Portable A-frame signage, branded stanchions, pavement decals for the Euclid Oval street activation, yellow palette | 1750
Daily Consumables & Spares Kit | Voucher paper rolls, cleaning supplies, sanitisation wipes, yellow touch-up paint, vinyl repair, gaffer | 2500
Custom Product Packaging (V3.1 — new) — 200 units | Yellow-palette product boxes, structural board, full-colour offset print, 300 × 200 × 70 mm, flat-packed for load-in. Per-unit scales linearly above 100; under 100 the per-unit cost climbs. | 4800
Subtotal — Branding, Signage & Consumables |  | 10000
Phase 04a — The Activation (Euclid Oval, 11 AM–8 PM, V3.1)
Inbound Logistics & Install | Truck, rigging hardware, 3-person install crew, permit-window supervisor, 4–6 hr install window | 5800
On-Site Technicians (V3.1 — extended to 8 PM) | Dedicated lead technician plus rotating second tech for rush windows and breaks, covering an extended 11 AM–8 PM operating window. Includes pre-open soundcheck and post-close shutdown. | 3000
Same-Day Strike & Outbound Freight | Complete de-installation, module breakdown, crated outbound freight within Euclid Oval's contracted strike window. Site walk-through with the Lincoln Road BID operations team. | 3300
Subtotal — The Activation (Euclid Oval) |  | 12100
Phase 04b — Logistics + Local Install at NYC Retail (V3.1)
Climate-Controlled Warehouse Hold | Secure climate-controlled storage at the AGV Miami NYC staging facility between Miami strike and NYC delivery | 2400
Inter-City Freight (Climate-Controlled Truck) | Miami → AGV Miami NYC staging facility with real-time GPS tracking, two-driver rotation, handoff documentation | 5500
Light Touchup After First Activation | Single light cosmetic touchup pass after the Miami activation: scuff/scratch repair, paint colour-match, lightbox edge cleanup, IVR/camera/printer functional re-test. Brief refurbish, not a full repaint. | 3000
White-Glove Delivery to NYC Retail Location | Climate-controlled final-mile delivery from AGV Miami NYC staging to the Client's nominated NYC retail address (Bond St assumed unless otherwise specified). Scheduled overnight or pre-open per store operations. | 2000
Retail-Environment Install Crew (V3.1 — new) | 2-person retail-environment install crew with floor-protection, retail-grade hand-tool kit, store operations liaison. 4-hour install window scheduled to avoid trading hours. | 2300
In-Store Fixture Setup (V3.1 — new) | Anchoring to retail-spec floor (no permanent penetration), electrical drop, IVR + camera + printer + lightbox bring-up, on-floor commissioning sign-off with the store manager. | 2100
Store Wayfinding & Footfall Driver Kit (V3.1 — new) | Sidewalk A-frame outside the store entrance, branded window-vinyl tease pointing to the Phone Box installation inside, in-store directional decals, and a printed/social CTA pack to drive walk-in footfall during the launch window. | 1000
Subtotal — Logistics + NYC Retail Install |  | 18300
Phase 05 — Project Management & Client Services
Project Management Fee | Dedicated senior producer, weekly status reporting, milestone tracking, Change Order administration, vendor / venue liaison, COI + insurance coordination, post-event reconciliation | 12000
Subtotal — Project Management |  | 12000
Gross Production Investment |  | 106750
Less: Preferred Partner Credit |  | -5000
NET V3.1 PRODUCTION INVESTMENT |  | 101750
PAYMENT TERMS
60% deposit ($61,050) due upon Client's written approval of this Scope of Work (Proposal execution). 40% balance ($40,700) due five (5) business days prior to first activation installation (on or before Friday, July 10, 2026). Payment exclusively via ACH electronic transfer or domestic wire transfer; ACH/wire details issued directly to the Client billing contact upon SoW approval. Reference GS-PHONEBOX-001 V3.1 on all remittances.
AGV Miami, LLC · 1440 Church St, Bohemia, NY 11716 · jclarkson@agvmiami.com · This invoice is issued in connection with proposal GS-PHONEBOX-001 V3.1 — proposed update, awaiting Client sign-off and incorporates by reference the executed Master Services Agreement between AGV Miami, LLC and Gymshark Ltd.